## Timeline
Week | Dates | Main Activity | Deadline | Responsible Person(s) | Completed (✔) | Priority
Week 41 | 07–13 Oct 2025 | Project kickoff, define topic, group roles, plan workflow | 2025-10-13 | Anders
Week 42 | 07–16 Oct 2025 | Collect data and develop a working model | 2025-10-16 |  |  | HIGH
Week 43 | 21–27 Oct 2025 | Test and analyze data; run initial models | 2025-10-27
Week 44 | 28 Oct–03 Nov 2025 | Refine analysis, interpret results, start report draft | 2025-11-03
Week 45 | 04–06 Nov 2025 | Finalize report, code appendix, reflection note | 2025-11-06
Week 46 | 07–13 Nov 2025 | Prepare and deliver final presentation | 2025-11-13